Semi-annual Progress Report for

Alaska Regional Observation System Coordination

NOAA Award NA08NOS4730287

November 1, 2008 – April 30, 2009

Prepared by Molly McCammon, AOOS Executive Director

May 27, 2009

This report briefly describes activities carried out in support of developing the Alaska Ocean Observing System (AOOS) and follows the format provided by the NOAA Coastal Services Center and Ocean.US.

1.0 	Project Summary

AOOS is the umbrella regional association (RA) for Alaska being developed as part of the national Integrated Ocean Observing System. AOOS has identified the user needs that are leading to development and integration of three geographically, culturally and economically diverse Regional Coastal and Ocean Observing Systems (RCOOSs) in the Gulf of Alaska, Bering Sea/Aleutian Islands and the Arctic Ocean. AOOS is being planned and implemented through the collective efforts of a consortium of users including academia, federal and state agencies, non-governmental organizations, marine research entities, subsistence users, community representatives, and industry.  The AOOS partners created a governance structure (with a Governance Committee) through a Memorandum of Agreement and established an AOOS Office with a Director co-located with the North Pacific Research Board in Anchorage.  AOOS funds are managed by the Alaska SeaLife Center (dba the Seward Association for the Advancement of Marine Science).  Since July 2003 AOOS staff and Governance Committee members have worked at a number of levels to further AOOS and the national Integrated Ocean Observing System (IOOS).  This project builds on those Phase I efforts by working to achieve the following Phase II objectives:

- Objective 1. Refining user needs assessments, formalizing stakeholder councils, and developing partnerships among users, data collectors and data managers across multiple agencies and disciplines.

- Objective 2.  Formalizing and refining governance and administrative structures, policies and procedures for a regional association that engages end users and coordinates with other observing efforts.

- Objective 3. Completing business and operations plans for the system to ensure that it will be cost-effective and sustainable.

- Objective 4. Continuing to plan for and implement a comprehensive integrated system that meets prioritized user needs for Alaska Statewide and its three major regions: Arctic, Bering Sea/Aleutian Islands, and Gulf of Alaska.

- Objective 5. Growing and sustaining the data management and communications subsystem.

- Objective 6. Building education, outreach and public awareness components that will ensure the results are effectively applied to address the identified issues.

- Objective 7.  Collaborating with other regional, national and international ocean observing initiatives.

Through its Phase I efforts, AOOS established an organizational structure and capacity with an interim governance structure, interim and draft plans, the backbone of a data system and web portal, and pilot observing systems. Phase II Planning efforts will, over the next three years, take AOOS to the pre-operational stage of developing a comprehensive, integrated system for Alaska.

Developing and sustaining a program of this nature depends on sustained collaboration and coordination with a multitude of governmental (both state and federal) and non-governmental efforts and entails significant startup costs.  Funding through this project is used to contribute to the costs of developing and sustaining the system including:  staff, office and related support costs, contractual support especially data management, website development and scientific support, travel and meeting costs for AOOS staff and committee members, and planning workshops. Other funding and in-kind resources will continue to be provided by the key partners in this consortium.

2.0	Progress and Accomplishments

2.1	User needs, stakeholder input, partnerships

- The issues and products that were used to develop the AOOS conceptual designs were based on regional stakeholder and user input from four years of outreach.  The AOOS board used that input as well as recommendations from the Scientific-Technical Team and the additional analysis provided through the socio-economic team’s process, to develop priorities for the 2008-2010 RCOOS proposal. The AOOS board asked that these priorities continue to be reviewed and refined, especially in light of funding availability and opportunities. Due to funding constraints, we were required to prioritize AOOS activities at the $1 million grant levels received in both the 2008 and 2009 budgets.

- Formal and informal contacts continue to be made with potential AOOS users/stakeholders in order to identify user needs and interests in AOOS and seek additional funding partners. We have been cautious with these efforts however, since sufficient IOOS funding has still not been included in federal budgets to support significant regional observing systems, especially given the geographic scale of Alaska and the paucity of existing ocean observing infrastructure.  We continue to be in a period of “expectation management.”   Our primary strategy continues to be looking for non-IOOS funds to start up programs while waiting for future IOOS funding.

- The following activities with various stakeholder/user groups occurred during this reporting period:

- Participation in development of Alaska’s Climate Change Strategy, including membership in technical working group on natural resources and ecosystems, membership in Research Needs Working Group and subpanel developing a proposed Climate Change Knowledge Center, with major reports due in June 2009;

- Participation as a formal partner with NOAA’s Alaska RISA (Alaska Center for Climate Assessment and Policy) and member of its Steering Committee;

- Participation in the state-federal Executive Roundtable on Climate Change – a group that meets about every 2 months to share their climate change program activities – including lead for the federal data integration initiative;

- Continued collaboration with MMS, oil and gas industry, and federal and state agencies to coordinate plans for ocean and coastal research and monitoring relating to offshore oil and gas development in the Beaufort and Chukchi Seas, including co-hosting the Arctic Research and Monitoring Workshop held January 22 in conjunction with the 2009 Alaska Marine Science Symposium which had more than 165 participants;

- Service on steering committee for annual Alaska Marine Science Symposium (attended by 500-600 marine scientists), including hosting of 3 workshops, 1 on climate change, 1 on the Prince William Sound Field Experiment, and the other on Arctic research and monitoring described above;

- Participation in Alaska Forum on the Environment (attended by 1200 people) February 2-5, including presentation on Arctic marine ecosystem changes panel;

- Participation in steering team developing a new Alaska contaminant monitoring program;

- Continued participation in NOAA’s regional collaboration team;

- Continued participation in Cook Inlet Regional Citizens’ Advisory Council including service as council president and member of Environmental Monitoring Committee (CIRCAC’s #1 priority is development of the Cook Inlet Ocean Observing System);

- Continued collaboration with the state-federal North Slope Science Initiative;

- Service as Cooperative Institute for Arctic Research (CIFAR) Fellow;

- Service on Alaska Sea Grant Program Advisory Committee, including hosting the bi-monthly Alaska Marine Policy teleconferences and assisting with reviewing research pre-proposals.

  - Governance and administrative structure, policies and procedures

- The AOOS Board’s annual meeting is scheduled for July 9, 2009. New officers will be elected and policies and procedures adopted. An informal review of AOOS priorities was delayed until fall 2009 following the summer Prince William Sound Field Experiment and in anticipation of a new 5-year contract with NOAA for the AOOS activities.

- The AOOS DMAC Committee met in Anchorage November 18.

- McCammon developed a job description and recruited for a newly created Program Partnership Coordination position.  This position will work on developing the partnerships necessary for expanding AOOS to Cook Inlet and Alaska’s Arctic.

- AOOS continues to actively participate in national IOOS planning efforts, including those of the National Federation of Regional Associations (NFRA), for which McCammon is chair. These activities included participation in NFRA executive committee meetings and monthly RA teleconferences, the NOAA IOOS education group and the IOOS regional performance metrics working group, regular meetings with the new NOAA IOOS Program Office leadership, planning for and participation in the annual meeting that was held in December 2008 in Baltimore, and planning for the next annual meeting to be held August 2009 in Seattle.  McCammon and NFRA Executive Director Josie Quintrell briefed the new NOAA Administrator Dr. Jane Lubchenco, as well as OMB staff Randy Lyons and Stu Levenbach and OSTP staff Jerry Miller.  McCammon also helped organize the IOOS Stakeholder/User briefing for House and Senate staffers held in Washington DC March 4.

2.3	Business/operations plan

- McCammon reviewed the draft journal article being prepared by the University of Alaska’s Institute of Social and Economic Research (ISER) describing the process used for developing the AOOS conceptual design priorities that included a suite of socio-economic criteria (costs, benefits, risks) as a second review filter.

- A board retreat to review the AOOS priorities has been delayed until fall 2009, following the summer Prince William Sound Field Experiment.

- McCammon has been participating in a Regional IOOS Performance Metrics Working Group that will help guide future program planning and development.

2.4	Regional Coastal Ocean Observing System Activities – planning, designing and implementing a comprehensive system

- Statewide:  The primary statewide role for AOOS is in data management and coordination with other observing activities.  McCammon continues to work with AOOS members and others to seek multiple and alternate sources of funding for AOOS, including partnering on several funding proposals submitted to other funding agencies. One proposal was submitted in partnership with The Nature Conservancy; another proposal was submitted with the University of Alaska and a host of other organizations nationwide to develop an Arctic Synthesis Collaboratory.

AOOS continues to be involved with numerous activities statewide:

- AOOS and the North Pacific Research Board are partnering on a project to develop a project and metadata browser and special mapping tools for Alaska waters called the Alaska Marine Information System.

- McCammon is an active participant in NOAA’s ARCTic Collaboration effort.

- NOAA RISA: Alaska Center for Climate Assessment and Policy – assisted with a fall 2008 workshop on sea ice products to be used by North Slope coastal residents, community planners & managers. AOOS staff gave a webinar presentation on our Alaska Marine Information System on March 17.

- Helped sponsor North Slope oil and gas and stakeholders workshop in Barrow Nov. 12-14, 2008.

- Working with Coastal States Organization and Alaska coastal management office to plan a fall workshop on how ocean observing can meet coastal manager needs in response to climate change impacts.

- Arctic:  With reduced funding for 2007-2008, the Barrow web cam and sea-ice radar were operated minimally with other funds.  AOOS continues to participate in other agency activities relating to the Arctic which will complement development of an observing system, including:

- Participation and coordination with the state-federal North Slope Science Initiative.

- Sponsorship of a workshop with state and federal agencies and the oil and gas industry to develop a strategy for Arctic Research and Monitoring.

- Bering Sea/Aleutian Islands:  The moorings in Bering Strait and Amukta Pass again will be deployed with other funding this year. Other activities include:

- Providing data support for the joint North Pacific Research Board and National Science Foundation’s Bering Sea Integrated Ecosystem Research Program.

- Use of the BSIERP as a case study for development of the Alaska Marine Information System (AMIS).

- Helped develop the Bering Strait case study for the Arctic Council’s Alaska Marine Shipping Assessment.

- Gulf of Alaska:  The focus continues on the Prince William Sound demonstration project, as well as furthering the preliminary efforts in Cook Inlet, the outer Kenai Coast, Kodiak, and Southeast.  Other activities include:

- The major field trial in Prince William Sound with the objective of testing the utility of an observing system for oil spill response and search and rescue is now scheduled for summer 2009.  Extensive planning meetings are now underway, including an onsite planning session slated for Valdez June 1.

- As president of the Cook Inlet Regional Citizens’ Advisory Council, McCammon continues to work on development of the Cook Inlet component of AOOS.  That project was identified as one of the top priorities for CIRCAC during its strategic planning process.

- Assisted in funding the UAF HF Radar team to install HF radar units at the base of Mt. Redoubt volcano in Cook Inlet to monitor ocean currents in the event of a catastrophic oil spill.

2.5	Data Management and Communications Subsystem

- The AOOS website completed a high level redesign.  Incorporation of required IOOS messaging elements.

- Development of the Alaska Marine Information System (AMIS) with the North Pacific Research Board: Initial project data integration has taken place.  A query and data ordering facility now exists for projects and data in the AOOS system and have associated project information.

- DMAC support and work for the Prince William Sound Field Experiment in 2009 is underway.  Reintegration of near real time assets into the IOOS backbone using the SOS DIF.

- AOOS is now actively archiving the Sea Ice Analysis in shapefile format from the Anchorage NWS ice desk.

- Surface current data from AOOS is currently temporarily available via NDBC.  The current HF radar installation is in support of potential oil spill mitigation efforts due to recent Mt. Redoubt volcanic activity.  The HF radar site will be moved to Prince William Sound for support of the field experiment.

- Explored implementation of the Google Map plug-in as a web application.  The Google Map plug-in seemed to be the most popular application for users of GLOS web portal.  The plug-in has met with failure for web portal users at AOOS.

- Recent product requests from students, data providers, private firms in support of private commercial projects:

- Sea Surface Temperature (Satellite)

- Chlorophyll-a (Satellite)

- Salinity (gridded climatology)

- Waves (gridded climatology)

- Individual station data for entire period of record (temperature, winds, water temperature); typically available from NDBC or NCDC

- Gulf of Alaska: GAK line (temperature, salinity, nutrient data)

- Barrow, AK ice radar and webcam data in AOOS storage

- The most popular format is geotiff for use in ESRI ArcMap for analysis.

- Support for the IOOS Program Office

- Implemented a bare bones SOS DIF web service for connecting AOOS near real time assets to IOOS.

- Implemented a rudimentary tool for showing the current state of partner SOS DIF services (http://ak.aoos.org/ioos/dif/index.html?svc=SOS).

- Participated in the IOOS DIF and Industry Day workshops in Silver Spring March 11-12, 2009.  Participated as a Steering Team member to develop materials and agenda for the workshop.

- Establishment of an ioos tech Google group to bring together partner programmers and implementers to provide and exchange information, code, cookbooks to ensure successful implementation of the IOOS backbone.  Increase partner collaboration at a very technical level.

- Partner teleconferences continue every two weeks.

2.6	Education, outreach and public awareness activities

- The AOOS website (www.aoos.org) continues to be updated with new data sets and information products.

- McCammon is the lead PI for the Alaska COSEE (Centers for Ocean Sciences Education Excellence) in partnership with the Alaska SeaLife Center, the Alaska Sea Grant Program, and the University of Alaska and funded by NSF.  This grant will fulfill a major portion of AOOS outreach goals and objectives, and AOOS will be working closely with the other eleven COSEE partners to share real-time data about ocean climate change in the north. The COSEE Alaska website (www.coseealaska.net) is being developed to be the major portal for education/outreach materials for Alaska ocean observing and ocean climate change.

- McCammon and AOOS Communications Director Nora Deans, who is also the COSEE Alaska Director, served on the Alaska SeaGrant Program’s search committee to carry out a national search for a marine education specialist as a faculty member of the University of Alaska Fairbanks School of Fisheries and Ocean Sciences and primary staff for COSEE Alaska.

- McCammon and Deans attended a national COSEE Council meeting at the new Sant Ocean Hall in the Smithsonian’s Natural History Museum in Washington DC November 4-7, 2008.

- McCammon and Deans met with other IOOS Regional Associations at a storytelling and data visualization workshop sponsored by NFRA, NSF, NOAA, and COSEE NOW in January 2009.

- The AOOS communication team, including AOOS Communications Director Nora Deans, regularly participates in monthly COSEE Council calls, in the Web Working Group calls and in New COSEE Center calls.

- Through COSEE Alaska, AOOS launched ocean science fairs in three coastal communities, and local winners competed at the Alaska State Science and Engineering Fair in March, where COSEE Alaska awarded prizes to marine science projects judged for both scientific and cultural merit.

- Deans has been participating in the IOOS Key Themes and Messages Working Group during this time frame as part of a national two-year effort.

- Deans is also participating in education committee meetings for NFRA and the NOAA Arctic Collaboration team. Deans is on the planning group for a meeting of NFRA education coordinators to be held in conjunction with the summer 2009 National Marine Educators Association meeting.

- Briefed North Pacific Research Board Advisory Panel and full Board on April 28 and 30 about status of AOOS.

- AOOS is collaborating on an online teacher’s guide in conjunction with a children’s book, Pete Puffin’s Wild Ride, which features Alaska’s currents. Published by Alaska Geographic, AOOS funds supported the donation of the book to every public school and library in Alaska.

- The Communicating Ocean Science Workshop at the Alaska Marine Science Symposium was expanded in 2009.  It was well attended by graduate students, scientists, educators and community members (www.alaskamarinescience.com). A meeting of SEANET (Scientists and Educators of Alaska Network) was held.

- Talks are also underway with the National Marine Educators Association for co-hosting the National Marine Educators Association’s national conference in the summer of 2012.

- We published the Alaska Ocean Observing System 4-page newsletter (Jan 2009), updated the brochure for the summer 2009 Prince William Sound Field Experiment, and created a communications and education and outreach plan.  We’re developing one-page stories about AOOS for IOOS.

- McCammon gave a presentation on AOOS and COSEE Alaska and the Communicating Ocean Sciences Workshop to the Interagency Working Group on Ocean Education February 2.

- AOOS partner Scott Pegau with the Oil Spill Recovery Institute gave a presentation on the PWS Field Experiment to a group connected remotely by video teleconferences on the 20th anniversary of the Exxon Valdez oil spill on March 24, 2009.

- We’re co-sponsored the Faces of Climate Change initiative – interviews with scientists and coastal residents talking about climate change science and impacts from western science and traditional knowledge perspectives.

2.7	National and international collaborations

- AOOS continues to collaborate with other regions in helping develop the regional components of a national IOOS.  These include participation in COL (Consortium for Ocean Leadership) activities including participation in their public policy committee, participation as a member of the Ocean Research Resources Advisory Panel (ORRAP), including co-chair of its ocean observing sub-panel, and ex-officio member of the federal Interagency Working Group on Ocean Observations (IWGOO). McCammon attended an ORRAP meeting in Washington DC December 4-5 and April 6-8. She co-chaired a joint meeting of the Ocean Observing Sub-panel of ORRAP and the IWGOO in Washington DC February 18. She attends by teleconference monthly IWGOO meetings.

- Other collaborations include:

- AOOS is participating in the activities of Arctic Observing Network (AON) and Sustained Arctic Observing Network (SAON), ensuring that AOOS is developed in line with any requirements that are developed in this process.  McCammon is a co-author of a white paper on Arctic observations that will be part of the OceanObs 09 conference in Venice, Italy in September.

- AOOS participated in the Arctic Council’s Arctic Marine Shipping Assessment, especially in writing several chapters of the Bering Strait case study. The final report is available at http://arctic-council.org/filearchive/amsa2009report.pdf.

- Scope of Work (Plans for the next year)

3.1.	Stakeholder/user needs identification and engagement new

- Continue with approach to three Alaska regions and sub-regions based on Large Marine Ecosystem (LME) concept.

- Continue to work with other collaborative efforts in Alaska such as NOAA’s Alaska regional collaboration team, the Alaska RISA (Alaska Center for Climate Assessment and Policy), the North Slope Science Initiative, the Exxon Valdez Oil Spill Trustee Council, the North Pacific Research Board, and the Alaska Marine Ecosystem Forum.

- Seek additional signatories to the AOOS MOA to bring additional stakeholders into the process.

- Continue to work with MMS, federal and state regulatory agencies, and oil and gas industry to coordinate plans for ocean and coastal research and monitoring relating to offshore oil and gas development in the Beaufort, and Chukchi Seas.

- Work with UAF remote sensing group on developing products for Alaska users.

- Work with Alaska Sea Grant to further user product development from Prince William Sound pilot project. Website tools configured specifically for sport fishing charter and recreational users have been constructed and reviewed internally. User testing in Anchorage and Fairbanks is scheduled for winter 2008/2009.

- Continue to participate in coastal erosion and coastal climatology planning efforts with the National Weather Service, NOAA climate office, and others.

- Participate in NOAA’s regional collaboration team and Hydrographic Services working group.

- Continue activities with CIRCAC Environmental Monitoring Committee.

- Participate in two Bering Sea/Bering Strait workshops – one in Seattle and one in Nome.

3.2.	Governance and administrative structure, policies and procedures

- Continue identifying new members for AOOS.  Work with Nominating Committee on officer slate and new member organizations in preparation for July 2009 meeting.

- Prepare operating procedures for AOOS board, committees and staff for adoption at July meeting.   Continue to evaluate need for 501 (c) (3) corporation, and if so, conduct legal work; and consider approach to scientific-technical advice and stakeholder/user committees based on LMEs along with committee mission and terms of reference.

- Participate in national IOOS activities that will be providing direction to the AOOS structure.

3.3.	Business/operations plans

- All of the components (Governance, DMAC, education & outreach, stakeholder engagement, and coastal observing system activities) continue to progress. The AOOS business/operations plan will integrate these efforts.

- The conceptual designs for the statewide functions and the 3 RCOOSs will continue to be reviewed and refined, with a special board retreat planned for fall 2009.

- We’ve been participating on a working group to develop performance metrics that will be used as guidance for developing regional implementation plans.  The metrics were a central focus of the IOOS Regional Workshop in Baltimore in December 2008.

- We will continue to participate in national planning activities that will be providing guidance and oversight to these plans.

- We will continue to collaborate on other proposals to secure funding for AOOS.

3.4.	Regional Coastal Ocean Observing System Implementation Activities

- Funding reductions in the AOOS RCOOS grant will require major reductions in current implementation activities.  The program has been cut in half, losing all programmatic elements outside of the PWS model development and DMAC activities.  This has resulted in a loss to the program of more than a year’s work and seriously compromised our ability to keep momentum going in Alaska.

- Following the board retreat and further review of the AOOS priorities, begin work on a Concept of Operations plan.

- Continue collaboration workshops and activities (data integration, sea ice, weather models, etc.).

- Statewide: The primary focus of AOOS continues to be development of its DMAC sub-system and education and outreach activities.

- Arctic RCOOS: AOOS is helping lead an initiative to develop an Arctic Research and Monitoring strategy with federal and state agencies, the oil and gas industry, and environmental interests.

- Bering Sea/Aleutian Islands RCOOS:  Continue to participate with NOAA, NPRB, USGS, and NSF on BSAI integrated research plans and proposals.  Continue to seek funding for coastal erosion initiatives in the Bering Sea and to provide input into the US Coast Guard’s Aleutians risk assessment that could lead to increased ocean observing platforms in Aleutians.

- Gulf of Alaska RCOOS: We will be testing the Prince William Sound models and forecasts during a field experiment this summer July 18 – August 3, 2009.

3.5.	DMAC activities

- Prince William Sound Field Experiment (July/August 2009)

- AOOS DMAC internal review Fall/Winter 2009

- Dataset integration into AOOS and IOOS backbone (Fall 2009-Summer 2010)

- Alaska Marine Information System

- Role Based Access Control

- Allow datasets and applications to be restricted

- Allow project and data mangers to manage access to projects and data

- Data and sensor information tracking for individual projects

- Development of more robust data visualization tool

- Regional Data Integration Framework (DIF)

- Requirement that AOOS bring 50% (by October 2009) and 100% of declared potentially available assets online for testing in October 2010.

- SOS DIF server will be the primary focus and will be nearly 100% compatible to the NDBC SOS DIF server.  The AOOS code and cookbook will be available for other partners to utilize.  Rob Cermak will be available to provide support for the code and cookbook at least by phone, email and the Google ioos_tech group.

- Consider replacement of Hyrax with THREDDS which will provide IOOS DIF WMS, WCS and DAP compatible data protocols.

- Actual DIF operational guidelines for WMS, WCS and DAP have yet to be identified beyond running a compatible OGC or DAP service.

- IOOS working group activities

- WSDE

- Regional DIF

- Observation Registry (partner and TAC member)

- Metadata Expert Team

- Archive Expert Team

- Integration of assets into AOOS and IOOS

- Bering Sea IERP, Wales (sea ice) (Western LME)

- Prince William Sound, Cook Inlet, Southeast AK (Southern LME)

- Barrow (sea ice), North Slope (Northern LME)

- Near real time assets, then historical and retrospective assets

- Development of continuous collaborations with web portal users and data providers

- Fishermen in SE AK (Southern LME; web portal)

- AMBCS/SnoTel (All LME regions; IOOS SOS DIF)

- Identify additional continuous collaborations around web portal products

- As a follow on to the web portal redesign, the data access pages need to be improved to reliably provide available AOOS information.  Pages and products that have active collaborations will be kept; the remaining pages will be taken offline and/or replaced.

3.6.	Education, outreach and public awareness activities

- Continue to develop outreach and public awareness plan, as part of AOOS business/implementation plan.

- Continue to work with Alaska Sea Grant MAP agent for PWS to hold stakeholder focus groups to improve PWS web page and user products.

- Implement Alaska COSEE proposal.

- Continue website development.

- Develop brochures and other publications.

- Use the Communicating Ocean Sciences workshop at the 2010 Alaska Marine Science Symposium to further AOOS outreach and education activities.

- Participate in education working group as part of NOAA Collaboration Team.

- Nora Deans will continue to participate in the NFRA education working group activities.

3.7 	Regional, national and international collaborations

- Continue participation in NFRA, ORRAP, COL, and IWGOO activities.

- Participate in Ocean Obs 09 conference planned for Venice, Italy in September 2009.

4.0	Leadership Personnel

- AOOS Senior Outreach Manager is no longer employed by the Alaska SeaLife Center, but instead, is funded directly by AOOS and the North Pacific Research Board with a new title: AOOS Communications Director.

- The newly created position of AOOS Program Partnership Coordinator will be filled beginning June 22.

- Budget Analysis

- All financial reports are up to date and have been submitted on time. A funding change was requested and approved for 2009 (funds taken from Sea Grant and science advice contracts) in order to create a full-time staff position – Program Partnership coordinator.