Semi-annual Progress Report for

Alaska Regional Observation System Coordination

NOAA Award NA08NOS4730287

May 1, 2009 – October 31, 2009

Prepared by 	Molly McCammon, AOOS Executive Director

Nora Deans, AOOS Communications Manager

November 30, 2009

This report briefly describes activities carried out in support of developing the Alaska Ocean Observing System (AOOS).

1.0 	Project Summary

AOOS is the umbrella regional association (RA) for Alaska being developed as part of the national Integrated Ocean Observing System. AOOS has identified the user needs that are leading to development and integration of three geographically, culturally and economically diverse Regional Coastal and Ocean Observing Systems (RCOOSs) in the Gulf of Alaska, Bering Sea/Aleutian Islands and the Arctic Ocean. AOOS is being planned and implemented through the collective efforts of a consortium of users including academia, federal and state agencies, non-governmental organizations, marine research entities, subsistence users, community representatives, and industry.  The AOOS partners created a governance structure (with a Governance Committee) through a Memorandum of Agreement and established an AOOS Office with a Director co-located with the North Pacific Research Board in Anchorage.  AOOS funds are managed by the Alaska SeaLife Center (dba the Seward Association for the Advancement of Marine Science).  Since July 2003 AOOS staff and Governance Committee members have worked at a number of levels to further AOOS and the national Integrated Ocean Observing System (IOOS).  This project builds on those Phase I efforts by working to achieve the following Phase II objectives:

- Objective 1. Refining user needs assessments, formalizing stakeholder councils, and developing partnerships among users, data collectors and data managers across multiple agencies and disciplines.

- Objective 2.  Formalizing and refining governance and administrative structures, policies and procedures for a regional association that engages end users and coordinates with other observing efforts.

- Objective 3. Completing business and operations plans for the system to ensure that it will be cost-effective and sustainable.

- Objective 4. Continuing to plan for and implement a comprehensive integrated system that meets prioritized user needs for Alaska Statewide and its three major regions: Arctic, Bering Sea/Aleutian Islands, and Gulf of Alaska.

- Objective 5. Growing and sustaining the data management and communications subsystem.

- Objective 6. Building education, outreach and public awareness components that will ensure the results are effectively applied to address the identified issues.

- Objective 7.  Collaborating with other regional, national and international ocean observing initiatives.

Through its Phase I efforts, AOOS established an organizational structure and capacity with an interim governance structure, interim and draft plans, the backbone of a data system and web portal, and pilot observing systems. Phase II Planning efforts will, over the next three years, take AOOS to the pre-operational stage of developing a comprehensive, integrated system for Alaska.

Developing and sustaining a program of this nature depends on sustained collaboration and coordination with a multitude of governmental (both state and federal) and non-governmental efforts and entails significant startup costs.  Funding through this project is used to contribute to the costs of developing and sustaining the system including:  staff, office and related support costs, contractual support especially data management, website development and scientific support, travel and meeting costs for AOOS staff and committee members, and planning workshops. Other funding and in-kind resources will continue to be provided by the key partners in this consortium.

2.0	Progress and Accomplishments

2.1	User needs, stakeholder input, partnerships

- Formal and informal contacts continue to be made with potential AOOS users/stakeholders in order to identify user needs and interests in AOOS and seek additional funding partners. We have been cautious with these efforts however, since sufficient IOOS funding has still not been included in federal budgets to support significant regional observing systems, especially given the geographic scale of Alaska and the paucity of existing ocean observing infrastructure.  We continue to be in a period of “expectation management.”   Our primary strategy continues to be looking for non-IOOS funds to start up programs while waiting for future IOOS funding.

- The following activities with various stakeholder/user groups occurred during this reporting period:

- Participation in development of Alaska’s Climate Change Strategy, including membership in technical working group on natural resources and ecosystems, membership in Research Needs Working Group and subpanel developing a proposed Climate Change Knowledge Center, with a major report submitted to the Governor’s Subcabinet on Climate Change in June 2009;

- Participation as a formal partner with NOAA’s Alaska RISA (Alaska Center for Climate Assessment and Policy) and member of its Steering Committee;

- Participation in the state-federal Executive Roundtable on Climate Change – a group that meets about every 2 months to share their climate change program activities – including lead for the federal data integration initiative;

- Participation in steering team developing a new Alaska contaminant monitoring program with an initial focus on mercury;

- Continued participation in NOAA’s regional collaboration team;

- Continued participation in Cook Inlet Regional Citizens’ Advisory Council including service as council president and member of Environmental Monitoring Committee (CIRCAC’s #1 priority is development of the Cook Inlet Ocean Observing System);

- Continued collaboration with the state-federal North Slope Science Initiative;

- Service as Cooperative Institute for Arctic Research (CIFAR) Fellow;

- Service on Alaska Sea Grant Program Advisory Committee, including hosting the bi-monthly Alaska Marine Policy teleconferences; and

- Planning for the 2010 Alaska Marine Science Symposium scheduled for Jan 18-22, including a special session on the PWS Field Experiment.

- Specific talks/presentations/workshop participation included:

- USGS workshop on Wildlife Climate Centers, Seattle, June 3-5 with 3 AOOS board members: Larry Hartig, John Goll & Leslie Holland-Bartels.

- Testimony at Marine Protected Areas Advisory Committee meeting in Anchorage Sept. 9-10.

- Co-hosted a workshop October 6-8 with Coastal States Organization and Alaska coastal management office on how ocean observing can meet coastal manager needs in response to climate change impacts.  More than 40 coastal managers, permitters and planners attended the workshop.

- Shorezone: Darcy Dugan participated in a ShoreZone partnership meeting in Juneau in October, plotting the next steps for a project that provides coastal habitat classification, inventory and mapping for Alaska’s intertidal and nearshore.

  - Governance and administrative structure, policies and procedures

- The AOOS Board met July 9, 2009 and reviewed the existing administrative structure and policies and procedures in light of the new Integrated Coastal Ocean Observing System Act.  Working groups were established to review the AOOS MOA and Policies and Procedures, as well as terms of reference for a new Stakeholders Advisory Panel.

- McCammon hired a new Program Manager in June.  Darcy Dugan will work on developing the partnerships necessary for expanding AOOS to Cook Inlet and Alaska’s Arctic.

- AOOS continues to actively participate in national IOOS planning efforts, including those of the National Federation of Regional Associations (NFRA), for which McCammon is chair (re-elected in August to another 2 year term). These activities included participation in NFRA executive committee meetings, monthly RA teleconferences, and the NFRA education group, regular meetings with the NOAA IOOS Program Office leadership, and planning for and participation in the annual meeting that was held August 25-27, 2009 in Seattle.  Substantial time has been spent in developing a national plan for the regional component of IOOS.

2.3	Business/operations plan

- A board retreat to review the AOOS priorities has been delayed until spring 2010.

- The national plan for the regional IOOS will help guide development of the next AOOS 5 year plan.

2.4	Regional Coastal Ocean Observing System Activities – planning, designing and implementing a comprehensive system

- Statewide:  The primary statewide role for AOOS is in data management and coordination with other observing activities.  McCammon continues to work with AOOS members and others to seek multiple and alternate sources of funding for AOOS. AOOS continues to be involved with numerous activities statewide:

- AOOS and the North Pacific Research Board are partnering on a project to develop a project and metadata browser and special mapping tools for Alaska waters called the Alaska Marine Information System.

- McCammon is an active participant in NOAA’s ARCTic Collaboration effort.

- NOAA RISA: Alaska Center for Climate Assessment and Policy.

- Arctic:  AOOS continues to participate in other agency activities relating to the Arctic which will complement development of an observing system, including:

- Participation and coordination with the state-federal North Slope Science Initiative;

- Participation in activities related to Arctic Observing Network and Sustained Arctic Observing Network;

- Attended the 2009 Ice Diminished Arctic conference in Annapolis June 9-11;

- Chaired a special session on the Arctic at the August ORRAP meeting;

- Visited Barrow with IOOS office director Zdenka Willis July 29, meeting with representatives of the Barrow Arctic Science Consortium, the Alaska Eskimo Whaling Commission, the North Slope Borough mayor’s office, and the Arctic Slope Regional Corporation.

- DMAC Team Lead Mark Johnson participated in Sustained Arctic Observing Network (SAON) data management workshop in Ontario.

- Attended MMS Arctic Technologies workshop in Anchorage Oct 13-15, International Arctic Fisheries Conference in Anchorage October 19-21, and Arctic Marine Shipping Assessment Workshop in Fairbanks October 22-24.

- Bering Sea/Aleutian Islands:  The moorings in Bering Strait and Amukta Pass again will be deployed with other funding this year. Other activities include:

- Providing data support for the joint North Pacific Research Board and National Science Foundation’s Bering Sea Integrated Ecosystem Research Program.

- Use of the BSIERP as a case study for development of the Alaska Marine Information System (AMIS).

- Provided assistance to Lee Cooper and NSF in developing a science plan for Bering Strait research and monitoring.

- Gulf of Alaska:  The focus continues on the Prince William Sound demonstration project, as well as furthering the preliminary efforts in Cook Inlet, the outer Kenai Coast, Kodiak, and Southeast.

- The major field trial in Prince William Sound with the objective of testing the utility of an observing system for oil spill response and search and rescue occurred July 17-August 3 2009. Post-experiment analysis is now underway.

- As president of the Cook Inlet Regional Citizens’ Advisory Council, McCammon continues to work on development of the Cook Inlet component of AOOS.  That project was identified as one of the top priorities for CIRCAC during its strategic planning process. Darcy Dugan has begun organizing a Cook Inlet modeling workshop for spring 2010.

2.5	Data Management and Communications Subsystem

- Development of the Alaska Marine Information System (AMIS) with the North Pacific Research Board is still in progress.

- The DMAC team provided substantial support to the Prince William Sound Field Experiment.

- Support for national IOOS

- Partner teleconferences continue every two weeks.

- Rob Cermak attended national DMAC meetings in Silver Spring in August.

- Reintegration of near real time assets into the IOOS backbone using the SOS DIF.

2.6	Education, outreach and public awareness activities

- The AOOS website (www.aoos.org) continues to be updated with new data sets and information products and a new press kit folder was designed and printed.

- AOOS communication team helped NOAA coordinate the national Ocean Policy Task Force meeting in Anchorage, designing materials, helping with registration and arranging for sign language interpretation at the meeting.

- The AOOS communication team, including AOOS Communications Director Nora Deans, regularly participates in monthly COSEE Council calls, in the Web Working Group and Excellence in Networking Tools sub-working group calls. McCammon participated in the national COSEE strategic planning effort.

- Deans, McCammon and COSEE educator Marilyn Sigman attended the COSEE Network meeting at Hilton Head, May 4-6.

- The AOOS communication team held two COSEE Alaska Advisory Council meetings, on June 2 and October 5, with participation from national COSEE leadership.

- Deans is also participating in education /outreach committee meetings for NFRA. Deans helped plan and attended a meeting of NFRA education coordinators held in conjunction with the summer 2009 National Marine Educators Association meeting and is participating in a series of webinars on exhibit development for getting real-time data into informal learning center interactive kiosks.

- AOOS reviewed and collaborated on an online teacher’s guide in conjunction with a children’s book, Pete Puffin’s Wild Ride, which features Alaska’s currents, which will be posted online in the next few months. Lesson plans are linked to national and state standards and Ocean Literacy Fundamental Principles. Published by Alaska Geographic, AOOS funds supported the donation of the book to every public school and library in Alaska.

- The Communications team maintained the website for the PWS Field Experiment; sponsored 3 community outreach events (Anchorage press conference July 16, Valdez public event July28, and Cordova open house July 15); and developed  a free-standing exhibit, brochures and handouts, as well as an August newsletter highlighting the experiment.

- AOOS team began planning the annual Communication Ocean Sciences Workshop at the 2010 Alaska Marine Science Symposium., co-hosted with COSEE Alaska and NPRB. COSEE Alaska is also sponsoring luncheon speakers at the AMSS.

2.7	National and international collaborations

- AOOS helped plan for and support the Federal Ocean Policy Task Force public meeting in Anchorage August 21.

- AOOS continues to collaborate with other regions in helping develop the regional components of a national IOOS.  These include participation in COL (Consortium for Ocean Leadership) activities including their public policy committee, participation as a member of the Ocean Research Resources Advisory Panel (ORRAP) until her term expired in August, including co-chair (and now, vice-chair) of its ocean observing sub-panel, and ex-officio member of the federal Interagency Working Group on Ocean Observations (IWGOO). McCammon attended an ORRAP meeting in Washington DC August 11-12. She attended by teleconference monthly IWGOO meetings.

- McCammon was appointed to the National Academy of Science’s Polar Research Board and attended the June 18-19 meeting in Washington DC.

- Other collaborations include:

- AOOS is participating in the activities of Arctic Observing Network (AON) and Sustained Arctic Observing Network (SAON), ensuring that AOOS is developed in line with any requirements that are developed in this process.

- McCammon is a co-author of a white paper on Arctic observations that was part of the OceanObs 09 conference in Venice, Italy in September that she also attended.

- Scope of Work (Plans for the next year)

3.1.	Stakeholder/user needs identification and engagement

- Continue with approach to three (now four per November board meeting) Alaska regions and sub-regions based on Large Marine Ecosystem (LME) concept.

- Continue to work with other collaborative efforts in Alaska such as NOAA’s Alaska regional collaboration team, the Alaska RISA (Alaska Center for Climate Assessment and Policy), the North Slope Science Initiative, the Exxon Valdez Oil Spill Trustee Council, the North Pacific Research Board, and the Alaska Marine Ecosystem Forum.

- Seek additional partners for AOOS.

- Continue to work with MMS, federal and state regulatory agencies, and oil and gas industry to coordinate plans for ocean and coastal research and monitoring relating to offshore oil and gas development in the Beaufort, and Chukchi Seas.

- Work with Alaska Sea Grant to further user product development from Prince William Sound pilot project.

- Continue to participate in coastal erosion and coastal climatology planning efforts with the National Weather Service, NOAA climate office, and others.

- Participate in NOAA’s regional collaboration team and Hydrographic Services working group.

- Continue activities with CIRCAC Environmental Monitoring Committee.

- Co-host Bering Sea/Bering Strait workshop in Nome in late January 2010.

- Establish Stakeholder/User Advisory Committee.

3.2.	Governance and administrative structure, policies and procedures

- Continue identifying new members for AOOS.  Work with Nominating Committee on officer slate in preparation for November 2009 meeting.

- Prepare operating procedures for AOOS board, committees and staff for adoption at November meeting.  Develop policies for competition, conflict of interest, and intellectual property rights.

- Participate in national IOOS activities that will be providing direction to the AOOS structure.

3.3.	Business/operations plans

- All of the components (Governance, DMAC, education & outreach, stakeholder engagement, and coastal observing system activities) continue to progress. The AOOS business/operations plan will integrate these efforts. Still waiting for final guidance on content and organizational template for the plan.

- The conceptual designs for the statewide functions and the 4 RCOOSs will continue to be reviewed and refined, with special thematic work sessions and a board retreat planned for spring 2010.

- We will continue to participate in national planning activities that will be providing guidance and oversight to these plans.

- We will continue to collaborate on other proposals to secure funding for AOOS.

3.4.	Regional Coastal Ocean Observing System Implementation Activities

- Following the board retreat and thematic working group sessions, the AOOS priorities will be reviewed and the next 3-5 year plan prepared.

- Continue collaboration workshops and activities (data integration, sea ice, weather models, etc.).

- Statewide: The primary focus of AOOS continues to be development of its DMAC sub-system and education and outreach activities.

- Arctic RCOOS: AOOS is helping lead an initiative to develop an Arctic Research and Monitoring strategy with federal and state agencies, the oil and gas industry, and environmental interests. Participate in AON design process.

- Bering Sea/Aleutian Islands RCOOS:  Continue to participate with NOAA, NPRB, USGS, and NSF on BSAI integrated research plans and proposals.  Continue to seek funding for coastal erosion initiatives in the Bering Sea and help with Nome workshop.

- Gulf of Alaska RCOOS: Assess results of PWS field experiment and make recommendations on what observations and models should be supported in future, and how to expand to Cook Inlet.

3.5.	DMAC activities

- Participate in analysis and reviews of Prince William Sound Field Experiment

- AOOS DMAC review Winter 2010

- Dataset integration into AOOS and IOOS backbone (Fall 2009-Summer 2010)

- Continued development of Alaska Marine Information System as primary user interface including Role Based Access Control and development of more robust data visualization tool

- Full implementation of regional Data Integration Framework (DIF)

- Participate in IOOS working group activities

- WSDE

- Regional DIF

- Observation Registry (partner and TAC member)

- Metadata Expert Team

- Archive Expert Team

3.6.	Education, outreach and public awareness activities

- Continue to develop outreach and public awareness plan, as part of AOOS business/implementation plan.

- Implement Alaska COSEE proposal.

- Continue website development.

- Develop brochures and other publications.

- Use the Communicating Ocean Sciences workshop at the 2010 Alaska Marine Science Symposium to further AOOS outreach and education activities.

- Participate in education working group as part of NOAA Collaboration Team.

- Nora Deans will continue to participate in the NFRA education working group activities.

3.7 	Regional, national and international collaborations

- Continue participation in NFRA, ORRAP, COL, IWGOO, AON and Polar Research Board activities.

4.0	Leadership Personnel

- The newly created position of AOOS Program Manager (Partnership Coordinator) was filled June 22 with Darcy Dugan.

- Budget Analysis

- All financial reports are up to date and have been submitted on time. Spending is on track.